{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":71,"n_cols":14,"rows_kept":71,"cut":false,"hidden":false,"merged":[[0,0,0,13],[1,1,1,13],[2,1,2,13],[3,7,3,8],[21,2,21,3],[22,2,22,3],[23,2,23,3],[24,2,24,3],[30,2,30,3],[31,2,31,3],[32,2,32,3],[33,2,33,3],[37,2,37,3],[38,2,38,3],[39,2,39,3],[40,2,40,3],[41,2,41,3],[42,2,42,3],[43,2,43,3],[44,2,44,3],[45,2,45,3],[46,2,46,3],[57,2,57,3],[63,2,63,3],[64,2,64,3],[65,2,65,3],[5,0,19,0],[21,0,46,0],[48,0,70,0],[5,1,15,1],[16,1,19,1],[22,1,44,1],[45,1,46,1],[48,1,62,1],[63,1,65,1],[66,1,68,1],[69,1,70,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,4,6],[3,9,4,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[34,2,36,3],[3,0,4,1],[25,2,29,3],[48,2,53,3],[58,2,62,3],[66,2,68,3],[69,2,70,3],[54,2,56,3]]}
["2020年度汇总"]
["目标","行业解决方案；团队组建、项目磨合"]
["决策","请求 → 评审 → 执行 → 反馈 → 迭代 (留档)"]
[null,null,"版本","边/云","描述","状态","年后计划","手机端",null,"大屏","Web后台","产品经理","项目经理","项目成员"]
[{"$nulls":7},"苹果","安卓"]
["产线","外","写字楼版","云","针对写字楼场景，有物业管理","第一版内测、苹果上线","● 跑通真实项目\n● 版本迭代","√","暂无","√","√","杨安东","杨安东","林鹏、杨安东、孟祥发、王崇宠、\n吕亮、冷坚、凌鲁冰、季建新"]
[null,null,"智能照明版","边云协同","针对商场照明","商场在用","● 局域网升级到能耗版\n● 手机端加载慢等问题","√","√","√","√","季建新","季建新","季建新"]
[null,null,"能耗版","边云协同","针对商场照明等","未启动","年后启动","暂无","暂无","√","√","季建新","季建新"]
[null,null,"物流版","边云协同","针对淮安物流","未启动","年后启动","暂无","暂无","√","√","丛晓磊"]
[null,null,"项目运营后台版","云","从讯飞项目开始，针对所有项目，\n做成SaaS平台","第一版内测","版本迭代","无","无","无","√","杨安东","杨安东","林鹏、杨安东、孟祥发、王崇宠、\n冷坚"]
[null,null,"开放平台版","云","针对所有设备，对第三方和内部开放","兼容HTTP,UDP","● 更多接口\n● 更多协议","无","无","无","√","季建新","季建新","季建新"]
[null,null,"中小企业版","云","针对中小企业，针对小B用电管理","暂缓"]
[null,null,"学生公寓版","云","针对学生宿舍用电管理","完成需求文档"]
[null,null,"铁塔基站版","云","针对铁塔用电管理","未启动"]
[null,null,"工地管理版","云","针对工地用电管理","未启动"]
[null,null,"学校、幼儿园版","云","针对学校的安全用电管理","未启动"]
[null,"内","总部运营后台版","云","管理所有模块、项目、关系等","第一版内测","版本迭代","无","无",null,"√","季建新","季建新","毛敏、吕亮、季建新"]
[null,null,"售后服务版","云","针对报警、维修处理","大屏内测","版本迭代","暂无","暂无","√","√","季建新","季建新","毛敏、季建新"]
[null,null,"缓存接口版","云","针对内部缓存处理","在用","版本迭代","无","无","无","无","季建新","季建新","季建新"]
[null,null,"运维监控版","云","针对基础设施、应用程序、发布等\n全方位监控","未启动"]
[]
["协同",null,"流程和方面",null,"规范和要求","现状","年后计划"]
[null,"流程","需求调研/市场反馈",null,"暂无"]
[null,null,"需求文档",null,"看懂：让设计、前端、后端看懂","人为沟通过多"]
[{"$nulls":4},"量化：做到什么程度","没有量化"]
[null,null,"任务分配",null,"分配到人","有"]
[{"$nulls":4},"任务要具体","不够具体"]
[{"$nulls":4},"任务可以量化","做得不够，应该出燃尽图"]
[{"$nulls":4},"任务优先级和关系","没有做好"]
[{"$nulls":4},"任务要有时限","做得不够"]
[null,null,"接口文档",null,"前后端认同统一"]
[null,null,"原型图",null,null,"缺少这环，成本高了"]
[null,null,"设计图"]
[null,null,"后端架构"]
[null,null,"后端开发",null,"单元测试"]
[{"$nulls":4},"集成测试"]
[{"$nulls":4},"压力测试"]
[null,null,"前端开发"]
[null,null,"移动端开发"]
[null,null,"前后端联调"]
[null,null,"内测"]
[null,null,"发布"]
[null,null,"测试环境",null,"多个测试点，工厂、办公室、其它"]
[null,null,"技术运维",null,null,null,"● 云平台选型\n● MySQL购买\n● TDEngine是否购买\n● 项目逐渐从测试服务器剥离"]
[null,null,"项目运维",null,null,"占有一定的时间"]
[null,"沟通","内部成员沟通",null,"尽量以文档为准","临时沟通过多"]
[null,null,"外协沟通",null,"尽量以文档为准","沟通成本高"]
[]
["架构","功能","可量化",null,"使用系统前后对比"]
[{"$nulls":4},"who"]
[{"$nulls":4},"when"]
[{"$nulls":4},"where"]
[{"$nulls":4},"how"]
[{"$nulls":4},"why"]
[null,null,"可视化",null,"支持灵活的展现方式"]
[{"$nulls":4},"元数据"]
[{"$nulls":4},"快"]
[null,null,"可控制",null,"开放平台"]
[null,null,"可追溯",null,"设备状态"]
[{"$nulls":4},"设备报警"]
[{"$nulls":4},"设备动作"]
[{"$nulls":4},"设备维修"]
[{"$nulls":4},"设备更换"]
[null,"数据源","漏传",null,"漏传检测机制"]
[null,null,"重复传",null,"去重处理"]
[null,null,"异构数据"]
[null,"存储","数据管理策略",null,"采集频次"]
[{"$nulls":4},"保留时长"]
[{"$nulls":4},"数据副本"]
[null,"计算","离线计算",null,"离线计算的组件"]
[{"$nulls":4},"电量电费计算策略"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}