{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":40,"n_cols":7,"rows_kept":40,"cut":false,"hidden":false,"merged":[[6,0,32,0],[6,1,13,1],[14,1,18,1],[19,1,22,1],[23,1,25,1],[26,1,27,1],[28,1,32,1],[6,2,7,2],[9,2,13,2],[14,2,16,2],[17,2,18,2],[19,2,22,2],[24,2,25,2],[26,2,27,2],[9,3,12,3],[14,3,16,3],[17,3,18,3],[19,3,22,3],[24,3,25,3],[26,3,27,3],[28,3,31,3],[17,4,18,4],[19,4,22,4],[28,4,31,4],[28,5,31,5],[28,6,31,6]]}
["环节","一级","二级","三级","问题/现状","解决方法/实施效果","是否解决"]
["需求文档"]
["任务分配"]
["接口文档"]
["原型图"]
["设计图"]
["后端","架构","分工协作",null,"公共领域层和项目领域层没有解耦导致开发时相互干扰。","公共领域层和项目领域层解耦","可以解决"]
[{"$nulls":4},"公共基础设施层和项目基础设施层没有解耦导致开发时相互干扰。","公共基础设施层和项目基础设施层解耦","可以解决"]
[null,null,"快速响应",null,"DDD领域驱动","灵活面对变化","已解决"]
[null,null,"解耦复用","系统解耦","项目业务和设备控制解耦，推出开放平台","开发不关心设备控制","已解决"]
[{"$nulls":4},"把项目应用程序内计算解耦出来，推出实时计算框架","开发灵活使用实时和离线计算","正在实践"]
[{"$nulls":4},"把缓存接口解耦出来，推出公共缓存接口","开发不关心缓存","已解决"]
[{"$nulls":4},"把报警数据解耦出来，汇总到售后服务系统","供给总部大屏、维修派单","已解决"]
[null,null,null,"架构解耦","不细说",null,"已解决"]
[null,"可用性","故障恢复",null,"服务器DOWN机","应用系统开启自启动","未解决"]
[{"$nulls":4},"应用程序不可用","看门狗停掉随即重启","未解决"]
[{"$nulls":4},"应用程序无法定时重启","定时重启应用程序","未解决"]
[null,null,"单点和集群",null,"云端模块数量增加会导致服务器压力","物理层面的负载均衡","未解决"]
[{"$nulls":5},"软件层面的负载均衡","未解决"]
[null,"性能","响应时间",null,"很多页面响应时间慢","使用云服务商关系数据库","未购买"]
[{"$nulls":5},"使用时序数据库","正在实践"]
[{"$nulls":5},"使用缓存数据库","未使用"]
[{"$nulls":5},"使用实时计算和离线计算","准备使用"]
[null,"监控","系统容量",null,"无法知道系统实时容量","监控内存、线程等","未解决"]
[null,null,"数据",null,"实时数据会有遗漏","使用实时计算平台实施监测","未解决"]
[{"$nulls":4},"电量数据会有遗漏或重复","电量处理机制","未解决"]
[null,"异常",null,null,"异常还不够明细","异常类型更加明细","未解决"]
[{"$nulls":4},"接口层使用得一个组件阻碍了异常的抛出","弃用该组件","未解决"]
[null,"测试","TDD测试驱动",null,"测试缺失","逐步采用","未解决"]
[null,null,"单元测试"]
[null,null,"集成测试"]
[null,null,"压力测试"]
[null,null,"测试数据",null,"实时数据、电量、报警等缺一份完整的模拟数据","时序数据库模拟一份完整的数据","未解决"]
["联调"]
["内测"]
["发布"]
["技术运维",null,"云服务商",null,"暂未购买华为云服务器","3.15购买","未解决"]
[null,null,"关系数据库",null,"暂未购买华为云关系数据库","3.15购买","未解决"]
[null,null,"时序数据库",null,"暂未购买华为云时序数据库","3.15购买","未解决"]
["项目运维",null,null,null,"手动运维耗时耗力","尽量自动化","未解决"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}